Annual Summary Report for Year 2015 and Plan for Year 2016

- Title of the Regional Initiative: Carpathian Wetland Initiative

__________________________________________________________________

- Work and activities undertaken during Year 2015

| objectives | activities | results/outputs | indicators |
| --- | --- | --- | --- |
| 1. Platform of basic data on wetlands | 1.1 Development of guidelines for wetland inventory based on experience in SK, collection of information on research of wetlands and projects | The pilot project in SK will be finalized by the end of II.2016, Guidelines on wetland inventory will be reviewed and translated in English in 2016); collection of data on wetland research and projects on wetlands conservation, management and restoration. | Database on Carpathian wetlands developed and improved; draft interactive map for SK on wetlands developed and tested |
|  | 1.2 Collection of data on threatened habitats and species and on invasive alien species in the Carpathians, meetings of experts | Consultations with the Implementation Committee of the Carpathian Convention on finalization of the draft Carpathian Red List of threatened habitats and species and the List of invasive alien species; work on the list of endemic plant species of the Carpathians; participation in the international workshop on invasive carnivores in wetlands (5-6 Mar. 2015, Mikulov, CZ) | Database of threatened habitats, species, endemic species and of invasive alien species in the Carpathians; report of the meeting |
|  | 1.3 Coordination of research activities with the Science for Carpathians (S4C) initiative, coordination with regional projects and with national institutions | Information exchange. | S4C Research Agenda 2015-2020 on the web |
| 2. Platform for cooperation | 2.1 CWI Board members and experts updating, electronic communication and consultations; Involvement of working group(s) of active practitioners, specialists and NGO representatives, national networks of experts and cooperating institutions, exchange of experts; Organizing of the CWI Board meeting during the Ramsar COP12 (Punta del Este, Uruguay, June 2015); participation in meetings of the Carpathian Convention bodies (including Biodiversity WG) and of other partners (WI, ICPDR) | List of CWI Focal Points; CWI Board Meeting during Ramsar COP12 (1 June 2015, Punta del Este, Uruguay), participation and presentations at important meetings of the Carpathian Convention (Implementation Committee, 24 Nov. 2015, Brussels, BE; Sustainable Tourism WG, Aggtelek NP, HU), cooperation with CC Secretariat in preparation of presentation on CWI for the opening conference of the Danube Transnational Programme, consultations with the Czech Ramsar Committee (V.,VI. and XII. 2015); participation and presentation in the Steering Committee meeting of the Alpine Convention (14-17 Oct. 2015, Berchtesgaden, DE) and discussion on future cooperation and projects; proposals to WI work programme; and electronic communication on relevant issues. | Report and minutes of the meetings |
|  | 2.2 Involvement of administrations of protected areas in the CWI work and cooperation with the Carpathian Network of Protected Areas (CNPA), the DANUBEPARKS Network, the Trilateral Ramsar Platform (AT-CZ-SK), WWF-DCP, IUCN (involvement in “Little Sydney” conference, May 2015, Hainburg, AT); CBD; stakeholders involvement | Carpathian protected areas administrations were informed and involved in the CWI project development, consultations on cooperation and possible joint projects with WWF, CEEweb for Biodiversity, DANUBEPARKS and Trilateral Ramsar Platform; cooperation with IUCN in preparation of the conference “Little Sydney” (28-31 May 2015, Hainburg, AT). | Minutes of the meetings |
|  | 2.3 Fund-raising and projects proposals for financing the Initiative in consultation with national institutions | Project proposal on ecological connectivity in the Carpathians (including wetlands) for funding from the EU Danube Transnational Programme was developed in cooperation with the Carpathian Convention Secretariat and partners in Carpathian countries, coordination meeting for potential partners was organized in SK (3 Sept. 2015, Banská Bystrica) | Expression of Interest for project ConnectGREEN submitted to the DTP; minutes of the meeting |
| 3. Platform for integrated river basin management especially in shared catchments | 3.1 Involvement in the preparation of relevant documents on sustainable and integrated water/river basin management of the Carpathian Convention | Declaration between ICPDR Tisza Group and the Carpathian Convention was prepared | Declaration |
|  | 3.2 Facilitation of bilateral consultations in shared wetlands and catchments on common objectives and principles of their management, pilot project, participation in international conferences | Bilateral consultations with SK-HU experts in transborder areas; presentation (poster) on CWI at the International conference Wetlands in Agricultural Landscape (11-14 Oct. 2015, České Budejovice, CZ) | Meetings of experts and stakeholders; reports of the meeting; book of abstracts |
| 4. Platform for wetland restoration activities | 4.1 Development of the wetland restoration strategies/policies, meetings; wetland restoration activities | Consultations on wetland restoration activities and possible projects with CEEweb for Biodiversity, participation in CEEweb Academy on building Blue-Green Infrastructure “Restoring and protecting wetlands and their ecosystem services” (6-8 Oct. 2015, Budapest, HU) | Meeting reports |
|  | 4.2 Sharing experience on wetland restoration in Europe | Participation in the study tour to successful restoration activities in Ramsar sites in the Czech Republic (17-20 May 2015); International conference on river and stream restoration REFORM 2015 “Novel Approaches to Access and Rehabilitate Modified Rivers” (Wageningen, NL, 30 June–2 July 2015) | Conference documents |
| 5. Platform for capacity building and public awareness | 5.1 Participation in a project on capacity building in protected areas; Development of the training programme on wetland management and restoration; establishment of a database of educational and training institutions and experts aimed at wetlands and communication with them; Development of the CWI programme of CEPA | Involvement in a project on capacity building plans for efficient protected area management in Eastern Europe, participation in meetings of Advisory Committee (Isle of Vilm, DE, 23-24 April 2015; Regensburg, DE, 27 Oct. 2015); training and capacity needs assessment (questionnaire developed, distributed and processed); visit of Visitor Centres UnterwasserReich in Nature park Hochmoor (AT) 17 May 2015 and Haus der Berge (Berchtesgaden, DE, 16 Oct. 2015); work on CWI CEPA programme | Minutes of the meetings, project documents |
|  | 5.2 Development of a project for training on identified priorities; support of other trainings | Work on a project draft, not finished yet; participation; distribution of information on training opportunities; meeting with environmental education employees in museum in Banská Bystrica on possibilities for development of education activities | Draft document |
|  | 5.3 Preparation and printing of a brochure and leaflet on CWI and Carpathian wetlands, translation of relevant guidelines; Maintenance of CWI web site and newsletter | CWI web site updating | CWI web site |
|  | 5.4 Operation of the regional Wetland Centre, building of its library, human capacities, improvement of facilities, CWI coordination | Carpathian Wetland Centre in Banská Bystrica maintained, but with no specially dedicated human resources, Carpathian wetland library supplemented; participation in the Collaborative Workshop of the Ramsar Regional Initiatives with the Convention Secretariat and the subsequent 51 Meeting of the Ramsar SC in Gland, CH (22-26 Nov. 2015) and consultations on improving effectiveness of RIs | Carpathian Wetland Centre, report of the meeting, decesions of the Ramsar SC 51 |

- Financial report for Year 2015

Summary of income and expenditures. Average exchange rate to CHF: 1.1

| Activities | Planned expenditures | Actual expenditure (EUR) |
| --- | --- | --- |
| 1.1 Wetland inventory guidelines | 1,000 EUR | 900.00 |
| 1.2 Collection of data on threatened habitats and species, IAS, endemic species in the Carpathians, meetings of experts | 6,000 EUR | 1,140.70 |
| 1.3 Coordination of research with the S4C, projects and national institutions | 1,000 EUR | 135.00 |
| 2.1 CWI Board members meetings during various events, Carpathian Convention meetings; working groups, exchange of experts | 8,500 EUR | 2,379.09 |
| 2.2 Cooperation with CNPA, DANUBEPARKS, WWF-DCP and Trilateral Ramsar Platform | 2,200 EUR | 792.00 |
| 2.3 Fund raising | 1,000 EUR | 1,989.63 |
| 3.1 Cooperation on documents on sustainable and integrated water/river basin management | 1,000 EUR | 0.00 |
| 3.2 Facilitation of bilateral consultations in shared wetlands, participation in conferences | 3,500 EUR | 1,351.94 |
| 4.1 Development of wetland restoration strategies / policies, meetings, workshops, restoration activities | 2,000 EUR | 604.20 |
| 4.2 Sharing experience on wetland restoration | 2,500 EUR | 2,976.51 |
| 5.1 Project on capacity building in Pas, training programme, database of educational and training institutions and experts, CEPA programme | 1,500 EUR | 1,458.20 |
| 5.2 Development of a project for training on priorities, support of trainings | 2,500 EUR | 180.00 |
| 5.3 Preparation and printing of publications, translations, maintenance of CWI web site and newsletter | 3,000 EUR | 180.00 |
| 5.4 Operation of the Carpathian Wetland Centre, library, improvement of human capacities, facilities, CWI coordination | 22,000 EUR | 6,359.44 |
| Total | 57,700 EUR | 20,446.71 |

| Sources of income | Income received (EUR) |
| --- | --- |
| SNC SR | 8,800.00 |
| CZ CWI budget | 2,096.78 |
| MoE Czech Republic | 1,070.00 |
| MoE Ukraine | 540.00 |
| MoE Hungary | 135.00 |
| UNEP SCC | 1,200.00 |
| ALPARC | 300.00 |
| NEOVISION project | 280.00 |
| CEEweb | 300.00 |
| WWF DCP | 250.00 |
| Propark, BfN | 500.00 |
| Ramsar core budget | 4,974.93 |
| Total | 20,446.71 |

Financial balance on 31 December 2015:  amount left to be carried over to 2016

Ramsar core budget		5,538.66 €

(+2,290 expected for second installment of 2015 not received yet)

CWI budget from Hungary		  5,716.78 €

CWI budget from the Czech Republic	     943.57 €

The Ramsar funding (including amount left from previous funding) was spent mostly for organization and travel expenses for meetings, participation in conferences (4,268.35 EUR) and maintenance and operation of the Carpathian Wetland Centre (706.58 EUR). It is proposed to use the amount left (about 7,829 EUR – 5,539 on the account and 2,290 expected as the second installment of 2015 contract from Ramsar) in 2016 for the activities planned for 2015 and 2016 according to the plan below.

- Work and activities planned for Year 2016

| Objectives | Activities | Results/outputs | Indicators |
| --- | --- | --- | --- |
| 1. Platform of basic data on wetlands | 1.1 Development of guidelines for wetland inventory, collection of information on research of wetlands and projects; cooperation in designation of new Ramsar sites in the Carpathian region and updating of Ramsar Information Sheets | Guidelines on wetland inventory in the Carpathian countries, database on wetland research and projects on wetlands conservation, management and restoration; Ramsar Information Sheets and maps elaborated for new Ramsar sites or updated RISs | Guidelines on Carpathian wetland inventory available on the web site; database; RISs for a number of Ramsar sites developed or updated |
|  | 1.2 Collection of data on threatened habitats and species and on invasive alien species in the Carpathians, meetings of experts | Database on threatened Carpathian wetland habitats and species and on the invasive alien species (IAS) for finalization of the Carpathian Red Lists, List of IAS and endemic species; results of meetings | Database of threatened habitats, species, endemic species and invasive alien species; meeting reports |
|  | 1.3 Coordination of research activities with the Science for Carpathians (S4C) initiative, participation in Forum Carpaticum (28-30 Sept. 2016, Bucharest, Romania), coordination with regional projects and with national institutions | Information on research of wetlands, experts and on projects, involvement in projects; presentation at Forum Carpaticum 2016 | Information available on the web site |
| 2. Platform for cooperation | 2.1 Update of the CWI strategy and work plan based on new Ramsar Strategic Plan and guidelines; CWI Board members and experts updating, electronic communication and consultations; Involvement of working group(s) of active practitioners, specialists and NGO representatives, national networks of experts and cooperating institutions, exchange of experts; Organizing the CWI Board meeting; participation in meetings of the Carpathian Convention bodies (including Biodiversity WG) and of other partners (WI, ICPDR) | Updated CWI strategy and work plan; updated list of CWI Focal Points; Presentations during important meetings; The working group and national networks communicated, national experts and Ramsar committees exchanges. One meeting of the CWI Board and electronic communication on relevant issues | Updated documents, list of national CWI focal points; Report/minutes of the meetings with results achieved; the working group and national networks of experts and institutions on the web, report of the exchange of experts and members of the Ramsar committees of the Carpathian countries |
|  | 2.2 Involvement of administrations of protected areas in the CWI work and cooperation with the Carpathian Network of Protected Areas (CNPA), the DANUBEPARKS Network, the Trilateral Ramsar Platform (AT-CZ-SK), WWF-DCP, IUCN, CBD; stakeholders involvement | Carpathian protected areas administrations informed and involved in the CWI projects, regular cooperation and information sharing with CNPA Steering Committee, DANUBE-PARKS, Trilateral Ramsar Platform, WWF-DCP, IUCN, CBD bodies and programmes and other networks and projects | A number of protected areas involved and informed; conferences results |
|  | 2.3 Fund-raising and projects proposals for financing of the Initiative in consultation with national institutions | Project proposals for funding and involvement in project drafts; analysis of funding opportunities for small grants | Project drafts submitted, involvement in different project proposals |
| 3. Platform for integrated river basin management especially in shared catchments | 3.1 Involvement in the preparation of relevant documents on sustainable and integrated water/river basin management of the Carpathian Convention | Documents developed, involvement in relevant projects, communication with the Carpathian Convention secretariat and ICPDR | Documents, meeting reports |
|  | 3.2 Facilitation of bilateral consultations in shared wetlands and catchments on common objectives and principles of their management, pilot project, participation in international conferences | Meetings of experts and relevant stakeholders; relevant projects implementation | A number of experts and national focal points participating; report of the conferences, recommendations; guidelines; results of the project, information distributed to partners |
| 4. Platform for wetland restoration activities | 4.1 Development of the wetland restoration strategies/policies, meetings, workshops; wetland restoration activities | Draft wetland restoration strategy/ policy in a country, data on barriers, meetings on the topic; small restoration activities | Draft document; meeting minutes; report on activities |
|  | 4.2 Sharing experience on wetland restoration in Europe | Workshops, conferences and study tours to wetland restoration examples; overview of wetland restoration guidelines and projects | Report of the meetings and study tour; information on the web |
| 5. Platform for capacity building and public awareness | 5.1 Development of the training programme on wetland management and restoration; establishment of a database of educational and training institutions and experts aimed at wetlands and communication with them; Development of the CWI program of CEPA | Training programme developed, using results of a study on capacity building in E Europe; database with information established and communication; CWI CEPA draft programme consulted with partners and existing Ramsar CEPA programme | Training programme; database on the web site; draft CWI CEPA programme on the web |
|  | 5.2 Development of a project for training on identified priorities; support of other trainings | Project proposal discussed and submitted, participation in trainings | Project draft or application |
|  | 5.3 Preparation and printing of a brochure and leaflet on CWI and Carpathian wetlands, translation of relevant guidelines; Maintenance of CWI web site and newsletter | A brochure and leaflet on CWI and the Carpathian wetlands and their functions and services, guidelines translated; web site updated with relevant information | Brochure and leaflet printed, guidelines in national languages and placed on the web; web site with updated information |
|  | 5.4 Operation of the regional Wetland Centre, building of its library, human capacities, improvement of facilities, CWI coordination | Wetland Centre maintained, functioning, Carpathian wetland library supplemented, staff supported; participation in the Working Group of the Ramsar Convention on the Ramsar Regional Initiatives | Wetland Centre operating and working for coordination and promotion of CWI and training; results and documents of the Working Group on the Ramsar Regional Initiatives |

- Financial plan for the year 2016

Summary of expected income and budgeted/planned expenditures. Average exchange rate to the CHF: 1.1

| Activities | Planned expenditures | Expected income and source (EUR) |
| --- | --- | --- |
| 1.1 Wetland inventory guidelines, designation of new Ramsar sites, updating of RISs | 1,500 EUR | SNC SR 500.00 MoE UA 500.00 Ramsar 500.00 |
| 1.2 Collection of data on threatened habitats and species, IAS, endemic species in the Carpathians, meetings of experts | 3,500 EUR | Ramsar 500.00 UNEP SCC 2,000.00 SNC SR 1,000.00 |
| 1.3 Coordination of research with the S4C, projects and national institutions, Forum Carpaticum | 1,200 EUR | Ramsar 700.00 SNC SR 500.00 |
| 2.1 Update of the CWI Strategy and work plan, CWI Board members meetings during various events, Carpathian Convention meetings; working groups, exchange of experts | 7,300 EUR | Ramsar 800.00 UNEP SCC 1,000.00 SNC SR 1,000.00 CWI budget HU 1,000.00 Moe CZ 500.00 MoE HU 500.00 MoE PL 500.00 MoE RO 500.00 MoE RS 500.00 MoE SK 500.00 MoE UA 500.00 |
| 2.2 Cooperation with CNPA, DANUBEPARKS, WWF-DCP and Trilateral Ramsar Platform | 2,200 EUR | Ramsar 500.00 SNC SR 500.00 MoE CZ 200.00 UNEP SCC 1,000.00 |
| 2.3 Fund raising | 1,000 EUR | Ramsar 500.00 SNC SR 500.00 |
| 3.1 Cooperation on documents on sustainable and integrated water/river basin management | 1,000 EUR | SNC SR 500.00 UNEP SCC 500.00 |
| 3.2 Facilitation of bilateral consultations in shared wetlands, participation in conferences | 3,000 EUR | Ramsar 500.00 MoE CZ 1,000.00 CWI budget HU 1,000.00 SNC 500.00 |
| 4.1 Development of wetland restoration strategies/ policies, meetings, workshops, restoration activities | 2,000 EUR | SNC SR 700.00 Ramsar 1,000.00 |
| 4.2 Sharing experience on wetland restoration | 2,500 EUR | Ramsar 800.00 MoE CZ 500.00 CWI budget CZ 500.00 SNC SR 500.00 |
| 5.1 Training programme, database of educational and training institutions and experts, CEPA programme | 1,000 EUR | MoE CZ 500.00 SNC SR 500.00 |
| 5.2 Development of a project for training on priorities, support of trainings | 2,000 EUR | SNC SR 500.00 Ramsar 500.00 MoE CZ 500.00 MoE UA 500.00 |
| 5.3 Preparation and printing of publications, translations, maintenance of CWI web site and newsletter | 3,000 EUR | SNC SR 1,000.00 Ramsar 1,000.00 UNEP SCC 1,000.00 |
| 5.4 Operation of the Carpathian Wetland Centre, library, improvement of human capacities, facilities, CWI coordination | 15,829 EUR | Ramsar 829.00 SNC SR 15,000.00 |
| Using the rest from Ramsar core budget |  | 7,829.00 EUR |
| Total | 47,029 EUR |  |

Jan Kadlecik

CWI co-ordinator

State Nature Conservancy of the Slovak Republic				28 February 2016

Acronyms:

AT		Austria

BfN		German Federal Agency for Nature Conservation

CBD		Convention on Biological Diversity

CEPA		Communication, Education, Participation and Awareness programme

CNPA		Carpathian Network of Protected Areas

CWI		Carpathian Wetland Initiative

CZ		Czech Republic

HU		Hungary

IAS		invasive alien species

ICPDR		International Commission for the Protection of the Danube River

MoE 		Ministry of Environment

PAs		Protected areas

PL		Poland

Propark		Propark Foundation, Romania

RIS		Ramsar Information Sheet

RO		Romania

RS		Serbia

S4C		Science for Carpathians

SC		Standing Committee

SK		Slovakia

SNC SR		State Nature Conservancy of the Slovak Republic

UA		Ukraine

UNEP SCC	UNEP Secretariat of the Carpathian Convention

WG		Working Group

WI 		Wetlands International

WWF-DCP	WWF Danube-Carpathian Programme