Annual Summary Report for Year 2017 and Plan for Year 2018

- Title of the Regional Initiative: Carpathian Wetland Initiative

__________________________________________________________________

- Work and activities undertaken during Year 2017

| Objectives | Activities | Results/Outputs | Indicators |
| --- | --- | --- | --- |
| 1. Platform of basic data on wetlands | 1.1 Development of guidelines for wetland inventory, collection of information on research of wetlands and projects; cooperation in designation of new Ramsar Sites in the Carpathian region and updating of RISs | Collection of data on wetland research and projects on wetlands conservation, management and restoration; consultations on proposals on new (transboundary) Ramsar Sites in the region | Database on Carpathian wetlands; interactive map of wetlands of Slovakia tested |
|  | 1.2 Collection of data on threatened habitats and species and on invasive alien species in the Carpathians, meetings of experts | Consultations within the Implementation Committee of the Carpathian Convention on review and finalization of the draft Carpathian Red List of threatened habitats and species and the List of invasive alien species; work on the list of endemic plant species of the Carpathians, inventory. | Database of threatened habitats, species, endemic species and of invasive alien species in the Carpathians; report of the meetings |
|  | 1.3 Coordination of research activities with the Science for Carpathians (S4C) initiative, coordination with regional projects and with national institutions | Information exchange. | S4C Research Agenda 2015-2020 |
| 2. Platform for cooperation | 2.1 Update of the CWI strategy and work plan based on new Ramsar Strategic Plan and guidelines; CWI Board members and experts updating, electronic communication and consultations; Involvement of working group(s) of active practitioners, specialists and NGO representatives, national networks of experts and cooperating institutions, exchange of experts; Organizing of the CWI Board meeting; participation in meetings of the Carpathian Convention bodies and WGs | List of CWI Focal Points updated; participation at important meetings of the Carpathian Convention (Implementation Committee, 15-16 June 2017, Modrá, CZ; COP5, Lillafüred, HU, 10-12 Oct. 2017), consultations on COP5 decision on CWI (COP5/4) and CC work plan; meeting with CWI Board members, potential partners for projects from Carpathian countries, discussion on work programme; visit of the representative of the Czech Ramsar Committee (SK, 8-10 Aug. 2017), consultations; electronic communication on relevant issues. | Report and minutes of the meetings, CC COP5 decisions |
|  | 2.2 Involvement of administrations of protected areas in the CWI work and cooperation with the Carpathian Network of Protected Areas (CNPA), the DANUBEPARKS Network, the Trilateral Ramsar Platform (AT-CZ-SK), WWF-DCP, IUCN, CBD; stakeholders involvement | Carpathian protected areas administrations were informed and involved in the joint project development; consultations on cooperation and possible joint projects with WWF, DANUBE-PARKS, ALPARC; participation at 15th meeting of the trilateral Ramsar Platform (5-6 Sep. 2017, Židlochovice, CZ), exchange of knowledge. | Minutes of the meetings |
|  | 2.3 Fund-raising and projects proposals for financing the Initiative in consultation with national institutions | Project proposal on peatland restoration in transborder regions of Carpathians for funding from Endangered Landscapes Programme developed and submitted in cooperation with CEEweb (HU), Daphne (SK), SNC SR (SK), Danube-Carpathian Programme (UA), CZ Nature Conservation Agency, nature conservation organizations in PL, the project was not approved; involvement in preparation of the project CentralParks for funding from INTERREG Central Europe in cooperation with EURAC (IT), SNC SR (SK), Pronatur (SK), Duna-Ipoly NP Directorate (HU), Ekopsychology Association (PL), European Wilderness Society (AT), Piatra Craiului NP Administration (RO); In cooperation with Ministry of Environment (CZ), SNC SR (SK), Danube-Carpathian Programme (UA) and other CWI Board members developed project on Ramsar Culture network development in the Carpathian region, consultancy agreement signed with the Ramsar Secretariat in October 2017. | Application forms for projects; Consultancy Agreement signed |
| 3. Platform for integrated river basin management especially in shared catchments | 3.1 Involvement in the preparation of relevant documents on sustainable and integrated water/river basin management of the Carpathian Convention | Cooperation between ICPDR and the Carpathian Convention; communication with ICPDR on project JOINTISZA, questionnaire filled in. | JOINTISZA project |
|  | 3.2 Facilitation of bilateral consultations in shared wetlands and catchments on common objectives and principles of their management, pilot project, participation in international conferences | Bilateral consultations with experts in transborder areas; cooperation with Duna-Ipoly NP Directorate (HU) on proposal for transboundary biodiversity management plan within the project planned - pilot action. | Meetings of experts and stakeholders |
| 4. Platform for wetland restoration activities | 4.1 Development of the wetland restoration strategies/policies, meetings; wetland restoration activities | Wetland restoration (Martina Eiseltová, Ivana Bufková), description of history of wetland degradation and summary of wetland restoration principles (focus on lakes, rivers, floodplains and peatland restoration) | Chapter of the book Wetlands - Ecology, conservation and sustainable use (H. Čížková, L. Vlasáková, J. Květ, eds, 2017) |
|  | 4.2 Sharing experience on wetland restoration in Europe | Participation in guided excursion on restoration activities in the Donau-Auen NP (Austria, 18-19 May 2017) within a LIFE project of BROZ (SK); participation in seminar on river restoration - sharing experience with Czech Nature Conservation Agency (Bratislava, SK, 5 Oct. 2017) |  |
| 5. Platform for capacity building and public awareness | 5.1 Development of the training programme on wetland management and restoration and CWI CEPA programme; establishment of a database of educational and training institutions and experts aimed at wetlands and communication with them; cooperation with IUCN WCPA WG on Capacity Development | Work on CWI CEPA programme; consultations with Ministry of Environment CZ on their leading role. |  |
|  | 5.2 Development of a project for training on identified priorities; support of other trainings | Identification of training and funding opportunities. |  |
|  | 5.3 Preparation and printing of a brochure and leaflet on CWI and Carpathian wetlands, translation of relevant guidelines; participation in Ekoplagat exhibition; Maintenance of CWI web site | Activities on production of leaflets and translation of guidelines included in projects drafts; participation in organization, co-funding and awarding the CWI price for the best poster on topic of wetlands in 14th Triennial EKOPLAGÁT´17 (June-Aug 2017, Žilina, SK); CWI web site updated | Ekoplagát website: http://www.npmalafatra.sk/ekoplagat/vysledky-2017/ CWI web site |
|  | 5.4 Operation of the regional Wetland Centre, building of its library, human capacities, improvement of facilities, CWI coordination | Carpathian Wetland Centre in Banská Bystrica maintained, but with no dedicated human resources, Carpathian wetland library supplemented; participation in the Working Group on the Ramsar Regional Initiatives, consultations on revised Operational Guidelines for RRIs. | Carpathian Wetland Centre, documents of the Ramsar Convention |

- Financial report for Year 2017

Summary of income and expenditure. Average exchange rate to CHF: 1.1

| Activities | Planned expenditures | Real expenditures (EUR) |
| --- | --- | --- |
| 1.1 Wetland inventory guidelines, designation of RS | 1,000 EUR | 180.00 |
| 1.2 Collection of data on threatened habitats and species, IAS, endemic species, meetings of experts | 3,000 EUR | 1,350.00 |
| 1.3 Coordination of research with the S4C, projects and national institutions | 1,000 EUR | 1,620.00 |
| 2.1 CWI strategy and work plan, Board members meetings, communication, Carpathian Convention meetings; working groups, exchange of experts | 7,000 EUR | 1,168.70 |
| 2.2 Cooperation with CNPA, DANUBEPARKS, WWF-DCP and Trilateral Ramsar Platform | 2,200 EUR | 1,110.00 |
| 2.3 Fund raising, project proposals | 1,000 EUR | 6,265.00 |
| 3.1 Cooperation on documents on sustainable and integrated water/river basin management | 1,000 EUR | 445.00 |
| 3.2 Facilitation of bilateral consultations in shared wetlands, participation in conferences | 2,000 EUR | 225.00 |
| 4.1 Development of wetland restoration strategies / policies, meetings, workshops, restoration activities | 1,000 EUR | 0.00 |
| 4.2 Sharing experience on wetland restoration | 2,500 EUR | 225.00 |
| 5.1 Training programme, database of educational and training institutions and experts, CEPA programme | 1,000 EUR | 105.00 |
| 5.2 Development of a project for training on priorities, support of trainings | 1,500 EUR | 0.00 |
| 5.3 Preparation and printing of publications, translations, Ekoplagat exhibition, maintenance of CWI web site | 3,000 EUR | 1,420.00 |
| 5.4 Operation of the Carpathian Wetland Centre, library, human capacities, facilities, CWI coordination | 16,098 EUR | 3,175.00 |
| Total | 43,298 EUR | 17,288.70 |

| Sources of income | Income received (EUR) |
| --- | --- |
| SNC SR SK | 9,543.70 |
| UNE CC | 1,520.00 |
| MoE CZ | 470.00 |
| MoE PL | 270.00 |
| MoE RO | 450.00 |
| WWF DCP | 420.00 |
| CZOS CZ | 135.00 |
| Danube Carpathian Program UA | 180.00 |
| Daphne SK | 420.00 |
| CEEweb HU | 600.00 |
| Eurac Research IT | 2,240.00 |
| UNEP GRID Warszaw PL | 500.00 |
| DINPI HU | 180.00 |
| Piatra Craiului NP RO | 210.00 |
| BROZ SK | 150.00 |
| Total | 17,288.70 |
| Ramsar project agreement | 2, |

Financial balance on 31 December 2017:  amount left to be carried over to 2018

Ramsar core budget					7,098.46 €

Ramsar-SNC project agreement (1st installment)		2,022.59 €

CWI budget from Hungary				5,673.06 €

CWI budget from the Czech Republic	   		   887.29 €

The Ramsar funding (amount left from previous funding – 7,098.46) was not spent in the reporting period and will be used for activities planned in 2018 according to the plan below.

- Work and activities planned for Year 2018

| Objectives | Activities | Results/outputs | Indicators |
| --- | --- | --- | --- |
| 1. Platform of basic data on wetlands | 1.1 Development of guidelines for wetland inventory, collection of information on research of wetlands and projects | Guidelines on wetland inventory in the Carpathian countries, database on wetland research and projects on wetlands conservation, management and restoration | Guidelines on Carpathian wetland inventory available on the web site; database |
|  | 1.2 Cooperation in designation of new Ramsar Sites in the Carpathian region and updating of RISs | Ramsar Information Sheets for designation/extension of Ramsar Sites, maps; updated RISs | RISs filled in, maps |
|  | 1.3 Collection of data on threatened habitats and species and on invasive alien species in the Carpathians, meetings of experts | Database on threatened Carpathian wetland habitats and species and on the invasive alien species (IAS) for finalization of the Carpathian Red Lists, List of IAS and endemic species; results of meetings | Database of threatened habitats, species, endemic species and invasive alien species; meeting reports |
|  | 1.4 Coordination of research activities with the Science for Carpathians (S4C), participation in Forum Carpaticum (15-18 Oct. 2018, Eger, HU); coordination with regional projects and with national institutions, implementation of the project Ramsar Culture Network in the Carpathians | Information on research of wetlands, experts and on projects, involvement in projects, result of the Ramsar Culture Network in the Carpathians project; proceedings of the Forum Carpaticum 2018 | Information available on the web sites |
| 2. Platform for cooperation | 2.1 Update of the CWI strategy and work plan based on the Ramsar Strategic Plan and guidelines; CWI Board members and experts updating, electronic communication and consultations; Involvement of working group(s) of active practitioners, specialists and NGO representatives, national networks of experts and cooperating institutions, exchange of experts; Organizing the CWI Board meetings – European Ramsar Regional Meeting (Olomouc, CZ, March 2018); Ramsar COP13 (Dubai, UAE, 21-29 Oct. 2018); participation in meetings of the Carpathian Convention bodies and WGs and of other partners | Updated CWI strategy and work plan; updated list of CWI Focal Points; Presentations during important meetings; The working group and national networks communicated, national experts and Ramsar committees exchanges. Meeting of the CWI Board and electronic communication on relevant issues | Updated documents, list of national CWI focal points; Report/minutes of the meetings with results achieved; the working group and national networks of experts and institutions on the web, report of the exchange of experts and members of the Ramsar committees of the Carpathian countries |
|  | 2.2 Involvement of administrations of protected areas in the CWI work and cooperation with the Carpathian Network of Protected Areas (CNPA), the DANUBEPARKS Network, the Trilateral Ramsar Platform (AT-CZ-SK), WWF-DCP, IUCN, Wetlands International, CBD; stakeholders involvement | Carpathian protected areas administrations informed and involved in the CWI projects, regular cooperation and information sharing with CNPA Steering Committee, DANUBEPARKS, Trilateral Ramsar Platform, WWF-DCP, IUCN, WI, CBD bodies and programmes and other networks and projects | A number of protected areas involved and informed; conferences results |
|  | 2.3 Fund-raising and projects proposals for financing of the Initiative in consultation with national institutions | Project proposals for funding and involvement in project drafts; analysis of funding opportunities for small grants | Project drafts submitted, involvement in different project proposals |
| 3. Platform for integrated river basin management especially in shared catchments | 3.1 Involvement in the preparation of relevant documents on sustainable and integrated water/river basin management of the Carpathian Convention | Documents developed, involvement in relevant projects (JOINTISZA), communication with the Carpathian Convention Secretariat and ICPDR | Documents, meeting reports |
|  | 3.2 Facilitation of bilateral consultations in shared wetlands and catchments on common objectives and principles of their management, pilot project, participation in international conferences | Meetings of experts and relevant stakeholders; relevant projects implementation | A number of experts and national focal points participating; report of the conferences, recommendations; guidelines; project draft, information distributed to partners |
| 4. Platform for wetland restoration activities | 4.1 Development of the wetland restoration strategies/policies; meetings, workshops; wetland restoration activities | Draft wetland restoration strategy/ policy in a country, data on barriers, meetings on the topic; small restoration activities | Draft document; meeting minutes; report on activities |
|  | 4.2 Sharing experience on wetland restoration in Europe | Workshops, conferences and study tours to wetland restoration examples; overview of wetland restoration guidelines and projects | Report of the meetings and study tour; information on the web |
| 5. Platform for capacity building and public awareness | 5.1 Development of the training programme on wetland management and restoration and CWI CEPA programme; establishment of a database of educational and training institutions and experts aimed at wetlands and communication with them; cooperation with IUCN WCPA Working Group on Capacity Development | Training programme developed; database with information established and communication; CWI CEPA and capacity development draft programme consulted with partners and existing Ramsar CEPA programme; | Training programme; database on the web site; draft CWI CEPA and capacity development programme on the web |
|  | 5.2 Development of a project for training on identified priorities; support of other trainings | Project proposal discussed and submitted, participation in trainings | Project draft or application |
|  | 5.3 Preparation and printing of a brochure and leaflet on CWI and Carpathian wetlands, translation of relevant guidelines; Maintenance of CWI web site | A brochure and leaflet on CWI and the Carpathian wetlands and their functions and services, guidelines translated; web site updated with relevant information | Brochure and leaflet printed, guidelines in national languages and placed on the web; web site with updated info |
|  | 5.4 Operation of the regional Wetland Centre, building of its library, human capacities, improvement of facilities, CWI coordination | Wetland Centre maintained, functioning, Carpathian wetland library supplemented, staff supported; participation in the W of the Ramsar Convention on the Ramsar Regional Initiatives | Wetland Centre operating and working for coordination and training; results and documents of the Working Group on the RRIs |

- Financial plan for the year 2018

Summary of income expected and budgeted/planned expenditure. Average exchange rate to the CHF: 1.17

| Activities | Planned expenditures | Expected income and source (EUR) |
| --- | --- | --- |
| 1.1 Wetland inventory guidelines, collection of information on research | 1,000 EUR | SNC SR 500.00 Ramsar 500.00 |
| 1.2 Designation of RS, update of RISs | 1,500 EUR | SNC SR 500.00 MoE UA 500.00 WWF DCP 500.00 |
| 1.2 Collection of data on threatened habitats and species, IAS, endemic species in the Carpathians, meetings of experts | 3,000 EUR | Ramsar 500.00 UNE SCC 2,000.00 SNC SR 500.00 |
| 1.3 Coordination of research with the S4C, projects and national institutions, Forum Carpaticum, Wetlands and Culture project | 9,918 EUR | Ramsar 500.00 Ramsar – project 3,418.00 SNC SR 500.00 CWI budget 5,500.00 |
| 2.1 Update of the CWI Strategy and work plan, CWI Board members meetings during various events, Carpathian Convention meetings; working groups, exchange of experts | 6,000 EUR | Ramsar 500.00 UNE SCC 1,000.00 SNC SR 1,000.00 Moe CZ 500.00 MoE HU 500.00 MoE PL 500.00 MoE RO 500.00 MoE RS 500.00 MoE SK 500.00 MoE UA 500.00 |
| 2.2 Cooperation with CNPA, DANUBEPARKS, WWF-DCP, WI, Trilateral Ramsar Platform, CBD | 2,200 EUR | Ramsar 500.00 SNC SR 500.00 MoE CZ 200.00 UNE SCC 1,000.00 |
| 2.3 Fund raising | 1,000 EUR | Ramsar 500.00 SNC SR 500.00 |
| 3.1 Cooperation on documents on sustainable and integrated water/river basin management | 1,000 EUR | SNC SR 500.00 UNE SCC 500.00 |
| 3.2 Facilitation of bilateral consultations in shared wetlands, participation in conferences | 1,500 EUR | Ramsar 500.00 MoE CZ 500.00 SNC SR 500.00 |
| 4.1 Development of wetland restoration strategies/ policies, meetings, workshops, restoration activities | 1,000 EUR | SNC SR 500.00 Ramsar 500.00 |
| 4.2 Sharing experience on wetland restoration | 2,500 EUR | Ramsar 1,000.00 MoE CZ 500.00 CWI budget CZ 500.00 SNC SR 500.00 |
| 5.1 Training programme, database of educational and training institutions and experts, CEPA programme | 1,000 EUR | MoE CZ 500.00 SNC SR 500.00 |
| 5.2 Development of a project for training on priorities, support of trainings | 1,500 EUR | SNC SR 500.00 Ramsar 500.00 MoE CZ 500.00 |
| 5.3 Preparation and printing of publications, translations, maintenance of CWI web site and newsletter | 3,000 EUR | SNC SR 1,000.00 Ramsar 1,000.00 UNE SCC 1,000.00 |
| 5.4 Operation of the Carpathian Wetland Centre, library, improvement of human capacities, facilities, CWI coordin. | 12,516 EUR | Ramsar 516.00 SNC SR 12,000.00 |
| Using the rest from Ramsar core budget Project Ramsar Culture Network |  | 7,098.00 EUR 3,418.00 EUR |
| Total | 49,134 EUR |  |

Jan Kadlecik

CWI coordinator

State Nature Conservancy of the Slovak Republic				15 January 2018

Acronyms:

| AT | Austria | PAs | Protected areas |
| --- | --- | --- | --- |
| BROZ | Bratislavské regionálne ochranárske združenie | PL | Poland |
| CBD | Convention on Biological Diversity | RIS | Ramsar Information Sheet |
| CC | Carpathian Convention | RO | Romania |
| CEPA | Communication, Education, Participation and Awareness programme | RRIs | Ramsar Regional Initiatives |
| CNPA | Carpathian Network of Protected Areas | RS | Serbia |
| COP | Conference of Parties | S4C | Science for Carpathians |
| CWI | Carpathian Wetland Initiative | SK | Slovakia |
| CZ | Czech Republic | SNC SR | State Nature Conservancy of the Slovak Republic |
| CZOS | Czech Ornithological Society | UA | Ukraine |
| DINPI | Duna-Ipoly National Park Directorate | UAE | United Arab Emirates |
| HU | Hungary | UNE SCC | UNE Secretariat of the Carpathian Convention |
| IAS | Invasive alien species | WG | Working Group |
| ICPDR | International Commission for the Protection of the Danube River | WI | Wetlands International |
| IUCN WCPA | IUCN World Commission on Protected Areas | WWF-DCP | WWF Danube-Carpathian Programme |
| MoE | Ministry of Environment |  |  |